WMO Task Team on QMS Action Item Log

| Completed Actions | Overdue Actions |
| --- | --- |

| Inaugural Meeting of the WMO Task Team on Quality Management Systems (Innsbruck, Austria, 10 – 13 October 2011) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Action Item No.: | Action Item: | Team Member Responsible: | Target Date for Completion: |  | Completed: |  | Comments on Status of Outstanding Action Items: |
| 1 | Investigate the possibility of conducting Ministerial meetings in all Regions to lift profile and engage Ministers. | WMO Secretariat | Ongoing |  | Completed |  | This issue will continue to be progressed as logistical and resource challenges allow. Replaced by Dedicated Country Visits involving also ministerial level |
| 2 | Professor Mieczyslaw S. Ostojski, advised he would provide personal support for any QM status questionnaires. | Professor Mieczyslaw S. Ostojski | TBA |  | Completed |  |  |
| 3 | Professor Mieczyslaw S. Ostojski requested a list from all Regions of the status of their QMS – refer item 5 for further information. | WMO Secretariat | _ |  | Completed |  |  |
| 4 | WMO Secretariat to amend the Terms of Reference (ToRs) in consultation with the CAeM Management Group and obtain confirmation from the team via e-mail. | WMO Secretariat | 04/11/2011 |  | Completed |  |  |
| 5 | Ongoing need for all team members to share their information on work within developing nations. The level of training, numbers trained, etc.input.doc | All TT Members | Ongoing |  | NA |  | CARRIED OVER TO MARRAKECH ACTION LOG |
| 6 | Establish a table of WMO Members that clearly articulates the country, the Met Authority, the Service provider and status of QM. | WMO Secretariat | 25/11/2011 |  | Completed |  | WMO Secretariat provided this to the group via e-mail on the 25/2/2012.This will be updated on an ongoing basis as a standing agenda item. |
| 7 | Draft a letter to the PR, Met Authority and Director/ Head of the Aviation Meteorological Service Provider to confirm the status of their adoption of a QM approach to the delivery of aviation weather services. | WMO Secretariat | 31/10/2011 |  | Completed |  | The letter has been drafted by the Task Team but details yet to be finalised on who will actually sign the letter. Replaced by Secretariat Questionnaire |
| 8 | Develop a brief questionnaire to be attached to the above correspondence that will provide a baseline set of data for the Task Team and WMO Secretariat and EC. | TT Members | 13/10/2011 |  | Completed |  |  |
| 9 | Secretariat to merge ICAO and WMO information within two weeks of receipt and provide a draft a diplomatic note/letter for appropriate level (President, Second Vice-President or SG) to forward to Members from whom information is incomplete by end October. | WMO Secretariat | 31/10/2011 |  | Completed |  |  |
| 10 | Within the next 2 years the team to provide recommendations for EC as to a proposed priority for assisting Members, for EC to present to Cg. | TT Members | End of 2012 |  |  |  | CARRIED OVER TO MARRAKECH ACTION LOG |
| 11 | Bryan to send a “Word” copy of the Guide to each member of the team. | Bryan | 18/10/2011 |  | 18/10/2011 |  | Sent with Minuted Actions |
| 12 | Each member of the team is to proof read and make amendments in “track change” and forward back to Bryan. Remember any changes apart from spelling and grammatical will be put to the team for a consensus decision. | TT Members | 28/10/2011 |  | Completed |  |  |
| 13 | Any offers for translation of the new QM Guide would be greatly appreciated and please contact the WMO Secretariat - Herbert. | TT Members | Ongoing |  | NA |  | French (with thanks to Canada) and Chinese (with thanks to Hong Kong) versions have been completed. CARRIED OVER TO MARRAKECH ACTION LOG |
| 14 | All Task Team members to fully assess the new WMO QM web page and as appropriate provide suggestions for improvements and or additional information to enhance the value of the website as a QM resource for Members. | TT Members | Initially 28/10/2011 then ongoing |  | Completed |  |  |
| 15 | Bryan and Helen to continue to pursue the establishment of an on-line QM forum on the new page with WMO and Bureau IT and web specialists. | Helen and Bryan | 28/10/2011 |  | Completed |  | Helen has a meeting with Bureau web and IT people Friday 21 October which at this time looks promising. However, B.L. Choy has advised that Hong Kong would be more than happy to provide and support a QM Forum site. |
| 16 | All Task Team members to “formally register” via e-mail (address is on the WMO website) to obtain the Username and Password for the new WMO-BoM QM website. | TT Members | 21/10/2011 |  | Completed |  | Only 3 TT members have formally registered at this time. It is imperative all Members do so. No requests external to the TT have been received as at 18 October 2011. All members were registered by the end of the meeting. |
| 17 | Develop strategies/ideas for consideration by the Team as to how the twinning partnership could work in your Region. | TT Members | 10 January 2012 - next TT meeting |  | Completed |  | This has been addressed under agenda items 6 and 7of Marrakech Agenda. Refer Appendix 6 of the Marrakech Minutes. |
| 18 | Review of the original letter to PRs (with the questionnaire) to include a new paragraph that highlights the risk analysis undertaken by the Task Team (see attached). | TT Members | 13/10/2011 |  | Completed |  |  |
| 19 | WMO Secretariat to provide a conclusion that summarizes the risk analysis. | WMO Secretariat | 21/10/2011 |  | 18/10/2011 |  | Completed and included in the TT minutes |
| 20 | Request will be made to the SG to invite Second Vice-President to the QM Co-ordination meeting at the WMO Secretariat to be conducted in Geneva to avoid the duplication of effort by other groups. | WMO Secretariat |  |  | Completed |  |  |
| 21 | Helen and Bryan to develop a specific Task Team web page within the WMO QM website. The page will be password protected and this information to be provided to only Task Team members. | Helen and Bryan | 28/10/2011 |  | Completed |  | This action was included post the TT meeting. The TT page will provide copies of the minutes, presentations, photos and this action log. Access will only be to Task Team Members. |
| Second Meeting of the WMO Task Team on Quality Management Systems (Marrakech, Morocco, 29 FebRUARY - 02 MarCH 2012) |  |  |  |  |  |  |  |
| Action Item No.: | Action Item: | Team Member Responsible: | Target Date for Completion: |  | Completed: |  | Comments on Status of Outstanding Action Items: |
| 22 | Investigate the possibility of conducting Ministerial meetings in all Regions to lift profile and engage Ministers. | WMO Secretariat | Ongoing |  | NA |  | This issue will continue to be progressed as logistical and resource challenges allow. Finances allocated for RAV. |
| 23 | Ongoing need to identify and clearly establish the QM status of all Members in the WMO Regions and share their information on work within developing nations. The level of training, numbers trained etc. Note: Members for each region are available at: http://www.wmo.int/pages/members/index_en.html | QMTT Region Reps and All TT Members | Ongoing |  | NA |  | Discussed and addressed in Agenda Item 4. Standing agenda item. |
| 24 | Draft a letter to the PR, Met Authority and Director/ Head of the Aviation Meteorological Service Provider to confirm the status of their adoption of a QM approach to the delivery of aviation weather services. | WMO Secretariat | 31/10/2011 |  | Completed |  | A copy of the final communication on this issue will be provided to the QMTT in the fullness of time by the WMO Secretariat. |
| 25 | Within the next 2 years the team to provide recommendations for EC as to a proposed priority for assisting Members, for EC to present to Cg. | TT Members | January 2014 |  |  |  | A draft recommendation on QMTT for the 2014 EC, will be provided to the next QMTT meeting for discussion. |
| 26 | Any offers for translation of the new QM Guide would be greatly appreciated and please contact the WMO Secretariat - Herbert. | TT Members | 15/3/2012 |  | Completed |  | The UK Met Office has completed translations in Spanish, Arabic and Russian. These plus the French and Chinese versions have not been published at this time (Carried over from Innsbruck Action Log - No.13) |
| 27 | Include on the WMO QM web page - "Publications" the cover of the ISO 19011:2002 Guidelines for auditing quality management systems. | Helen | 15/03/2012 |  | 15/3/2012 |  |  |
| 28 | Investigate the feasibility of creating topic themes within the Yammer Forum that align with the ISO 9001 clauses and other related QM topics. | Helen | 01/05/2012 |  | 19/4/2012 |  |  |
| 29 | Develop an "open" WMO QM web page portal to attract new members. | Helen | 01/05/2012 |  | 28/3/2012 |  |  |
| 30 | Investigate the legal implications of posting the contact details of all registered users on the "closed" WMO QM web page. | Helen | 01/05/2012 |  | Completed |  | The BoM legal team advised that contact details could not be posted on the website unless authorised by those individuals. |
| 31 | Investigate if the WMO QM web site can host an FTP facility for sharing large documents between members. | Helen | 01/05/2012 |  | Completed |  | www.govdex.gov.au has been set up but not tested. There may not be a need to facilitate this. |
| 32 | Post the reviewed Risk Analysis on the WMO QM website in the WMO French, English and Spanish. The Risk Analysis to be forwarded to Olga, Alain and Rodrigo for translation. The post is to be accompanied by a disclaimer pertinent to the validity of the assumptions made during the risk analysis process. | Helen and Bryan Olga, Alain and Rodrigo | 01/05/2012 |  | Completed |  |  |
| 33 | Respond to the JCOMM request to advise on the WMO QM TT's activities on identifying competencies as per 6.2 of the ISO 9001. | Bryan | 31/03/2012 |  | Completed |  | Bryan is now leader of the JCOMM Marine Competency Requirements Task Team |
| 34 | QMTT members to provide QM implementation success stories for posting on Yammer. | TT Members |  | NA | 11/3/2012 | Geofrid advised he would post a success story relevant to Tanzania as soon as possible. |  |
| 35 | All WMO QMTT to update their profiles to ensure that the country is stated. | TT members |  | NA | Completed | Closed |  |
| 36 | All WMO QMTT members to ensure that the WMO QMTT URL is articulated on all QMTT correspondence. | TT Members |  | NA |  | WMO Secretariat, Helen and Bryan will develop a correspondence template for distribution to the QMTT. |  |
| 37 | All QMTT members to provide the URL of "parent" organizations that oversee the activities of certification bodies and auditors in their region. For example: IAF, IRCA. | Helen |  | 31/03/2013 |  | Helen to provide the URL to certification bodies that are provided on the ISO web site. The URL will be provided on the WMO QM website. |  |
| 38 | All TT members to review the strategies they are responsible for under Appendix 6 "Strategies to engage and enhance the development and implementation of QM for WMO members" and report back to the TT accordingly. | TT Members |  | As per Appendix 6 | Completed |  |  |
| Third Meeting of the WMO Task Team on Quality Management Systems (Melbourne, Australia, 05 – 08 March 2013) |  |  |  |  |  |  |  |
| Action Item No.: | Action Item: | Team Member Responsible: |  | Target Date for Completion: | Completed: | Comments on Status of Outstanding Action Items: |  |
| 39 | Helen to facilitate the removal of the password protection from the WMO QM website. However, a message on the opening page will strongly encourage people to register so as to ensure they are notified of updates. | Helen |  | 31/03/2013 | Completed |  |  |
| 40 | Convert the BoM Conformity Assessment Tool into a generic template for use by WMO Members. Its existence will be notified on the WMO QM Forum and website. | Helen and Bryan |  | 30/05/2013 | Completed |  |  |
| 41 | Raise the WMO QMTT's concern at the lack of formal qualification requirements underpinning the competence framework for aeronautical met observers. | WMO Secretariat |  | ASAP |  |  |  |
| 42 | Create a link to the cost recovery expert team on governance and partnership from the WMO QM website. | Helen and WMO Secretariat |  | Ongoing |  | Helen will post the link on the WMO QM web site. |  |
| 43 | Post a link to the ICAO Safety Management System documentation on the WMO QM web site. For example: ICAO Safety Management System Manual. | Helen |  | 30/05/2013 | Completed |  |  |
| 44 | Source/write a document that identifies the links between the various ISO standards that impact on the delivery of weather and ocean services. For example: risk management, OH&S and QM. | Helen, Bryan and Gerold |  | December 2013 |  | Gerold to present at the next QMTT |  |
| 45 | Identify additional guidance material to be included as appendices to the QM Guide for specific application areas such as "defining user requirements"; "verification" and "competence". Identification of the additional guidance will be sourced from the Technical Commission QM focal points. | WMO Secretariat |  | Ongoing |  | WMO QMTT is currently awaiting nominations and terms of reference from these groups. |  |
| 46 | Expand the availability of guidance material on ISO 19011 to enhance auditor skills. Mario Lentiz from Austro Control has published a guidance document in German – investigate the possible translation of this into the 6 WMO working languages for publication. | Gerold |  | 30/06/2013 |  |  |  |
| 47 | WMO QMTT to broaden the scope of its focus and activities to include other areas apart from aviation in its deliberations. For example: marine, disaster mitigation, public, agriculture, etc. | QMTT Members |  | Ongoing |  |  |  |
| 48 | Confirm date and location for next QMTT Meeting. | WMO Secretariat |  | 30/06/2013 | Completed | Geneva 2015 |  |
| 49 | QMTT and WMO Secretariat to investigate QMS status of Group A Members (refer Table **) by correspondence with an offer to provide on-site evaluation. | WMO Secretariat |  | 30/06/2013 |  |  |  |
| 50 | Investigate the establishment of evaluation teams in terms of membership, expertise and terms of reference. | WMO Secretariat |  | 30/06/2013 |  |  |  |
| 51 | A two page report to be submitted to EC after the completion of stage 2 of the AusAID QM Project. | Bryan and Helen |  | September 2013 | Completed |  |  |
| 52 | Although the aeronautical competency framework is recognised there is now the need to develop a generic assessment tool to fully assess competence. A recommendation to be forwarded to the Training Task Team on this issue. | WMO Secretariat |  | 30/06/2013 |  |  |  |
| 53 | Provide a brief paper (one page) on the status of the WMO Quality Management Task Team for EC. Provide dot points for Prof. Ostojski together with the WMO QMTT Action log. | Bryan |  | 30/04/2013 | Completed |  |  |